## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2235-swen-261-04-2b-2bOrNot2b
Testing Team Name | fill in when doing cross-team testing
ONLINE GOOGLE COPY: | https://docs.google.com/spreadsheets/d/1vO0eVwZBUQFAySi8gz2k9njD7NZCklr5aNXf1g1ek-E/edit?usp=sharing
NOTE: There's an excel viewer extension for VS Code that we can use to edit this without having to use the above link

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. (NOTE: This given example appears to be a copy of the Story: Browse Needs story that we have in Trello) | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Story: Proceed to Checkout | Passed ✅ (AC)
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Story: Data Persistence - Cart | Passed ✅ (AC)
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Story: Add/Remove Needs From Cart | Passed ✅ (AC)
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Story: Log In Helper | Passed ✅ (AC)
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Story: Log In Admin | Passed ✅ (AC)
As a helper I want to proceed to checkout so that I can complete the required transactions for the items in the cart. (Story: Proceed to Checkout) | Given that I am on the u-fund site when I am not on the Checkout page then I must see a means to navigate to the Checkout page. | Story: Browse Needs | Passed ✅ (AC)
Given that I am not on the Checkout page when I choose the Checkout page then I am taken to the Checkout page.
Given that I am on the Checkout page when there are no Needs in the Cart then I get a message indicating that the Cart is empty.
Given that there is one or more Need(s) in the Cart, there should be a button that can be used to complete the transaction.
Given that I am attempting a transaction on the Checkout page, the total cost of the transaction and any other related information should be made readily apparent.
Given a transaction occurs successfully, the Needs should be appropriately removed from the Cart and Cupboard.
As a HELPER I want to MODIFY A CART so that I CAN CHOOSE WHICH NEEDS TO ADD OR REMOVE. (Story: Data Persistence -- Cart) | Given that I am on the u-fund site when I am logged in as a Helper then I can view a list of Needs to add to / remove from a Cart.
Given that I am on the u-fund site when I am logged in as an Admin then I can NOT view a list of Needs to add to / remove from a Cart.
Given that I am viewing a list of available Needs (the Cupboard) when I am logged in as a Helper, then I can click an "Add to Cart" button to add a copy of a Need to the Cart.
Given that I am viewing a list of Needs which I have already added (the Cart) then I can click a "Remove" button to remove that Need from the Cart.
As a HELPER I want to LOG IN so I can DONATE. (Story: Log In Helper) | Given I AM A HELPER when I LOG IN then I EXPECT TO BE ABLE TO VIEW NEEDS AND DONATE.
Given I AM A USER VIEWING THE SITE when I WANT TO LOGIN then I CAN ENTER CREDENTIALS TO CONTINUE
Given I HAVE ENTERED MY CREDENTIALS when I CLICK THE "Login" BUTTON then I CAN SEND A REQUEST TO LOGIN WITH THE GIVEN CREDENTIALS
Given I AM LOGGED IN when I CLICK THE "Log Out" BUTTON I AM LOGGED OUT AND TAKEN BACK TO THE LOGIN PAGE
As an ADMIN I want to LOG IN so that I CAN MODIFY/MANAGE THE SITE. (Story: Log In Admin) | Given I am an ADMIN when I LOG IN then the system should allow me to modify the pertinent materials
Given I am an ADMIN when LOG IN then I should be able to LOG OUT to see the changes